Malahide Casino

Refurbishment and Extension to accommodate The Fry Model Railway Exhibition

Fingal County Council has recently appointed CTS Projects Limited as contractor to undertake a series of enabling works at the Casino. They expect to mobilise week beginning 17/07 with expected completion within four weeks.

This phase of enabling works involve:

- Site investigation and testing works to assist on design development and tender documents

- The cutback of the ivy covering external walls

- Temporary roof protection measures to address roof weakness at ridge and valleys  to remain in position for approx. 6 months until follow on main contract refurbishes the roof and thatching

- A finished site hoarding to secure the existing cottage and the construction site area with information signage panels which will remain in position until the permanent refurbishment works are complete.

Design development and tender documentation for the refurbishment and permanent extension is progressing well. Fire safety certificate and Disability access certificate consent processes are pending and the project remains on programme to go to tender in late September 2017.

It is expected to have a main contractor appointed in December 2017 with construction project duration of approximately 12 months.

The programme of refurbishment works on the Casino cottage is extensive, including extensive heritage and conservation works on walls, joinery, rethatching, complete services upgrade within the building and across the site. A temporary over roof of the existing cottage is being considered during the contract  to facilitate the conservation works within the tightest possible timeline.

The modern extension is being designed in accordance with best practice sustainable development and be highly energy efficient and naturally ventilated.

Separately an exhibition team will be appointed to deliver on the design and installation of an exciting layout within the new spaces at the Casino for the new Fry Model Railway experience incorporating working layouts and modern interactive interpretation and display.